## Burndown Chart
Team
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-02-01 | 100 | 2022-02-01 | 100
2022-02-02 | 78.9444 | 2022-02-02 | 85.7143
2022-02-03 | 62.2778 | 2022-02-03 | 71.4286
2022-02-04 | 33.1389 | 2022-02-04 | 57.1429
2022-02-05 | 26.1944 | 2022-02-05 | 42.8571
2022-02-06 | 10.0833 | 2022-02-06 | 28.5714
2022-02-07 | 5.6944 | 2022-02-07 | 14.2857
2022-02-08 | 1.3056 | 2022-02-08 | -1.3334e-10
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-02-01 | 100 | 2022-02-01 | 100
2022-02-02 | 91.7143 | 2022-02-02 | 85.7143
2022-02-03 | 77.7143 | 2022-02-03 | 71.4286
2022-02-04 | 34.1429 | 2022-02-04 | 57.1429
2022-02-05 | 34.1429 | 2022-02-05 | 42.8571
2022-02-06 | 13.4286 | 2022-02-06 | 28.5714
2022-02-07 | 13.4286 | 2022-02-07 | 14.2857
2022-02-08 | 13.4286 | 2022-02-08 | -1.3334e-10
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
| 100 | 2022-02-01 | 100
2022-02-02 | 91.7143 | 2022-02-02 | 85.7143
2022-02-03 | 72.4286 | 2022-02-03 | 71.4286
2022-02-04 | 34.8571 | 2022-02-04 | 57.1429
2022-02-05 | 34.8571 | 2022-02-05 | 42.8571
2022-02-06 | 14.1429 | 2022-02-06 | 28.5714
2022-02-07 | 14.1429 | 2022-02-07 | 14.2857
2022-02-08 | 14.1429 | 2022-02-08 | -1.3334e-10
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-02-01 | 100 | 2022-02-01 | 100
2022-02-02 | 73.6667 | 2022-02-02 | 85.7143
2022-02-03 | 52 | 2022-02-03 | 71.4286
2022-02-04 | 27.8333 | 2022-02-04 | 57.1429
2022-02-05 | 25.17 | 2022-02-05 | 42.8571
2022-02-06 | 7.67 | 2022-02-06 | 28.5714
2022-02-07 | 7.67 | 2022-02-07 | 14.2857
2022-02-08 | 7.67 | 2022-02-08 | -1.3334e-10
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-02-01 | 100 | 2022-02-01 | 100
2022-02-02 | 79.41 | 2022-02-02 | 85.7143
2022-02-03 | 79.41 | 2022-02-03 | 71.4286
2022-02-04 | 25.52 | 2022-02-04 | 57.1429
2022-02-05 | 25.52 | 2022-02-05 | 42.8571
2022-02-06 | 9.93 | 2022-02-06 | 28.5714
2022-02-07 | 9.93 | 2022-02-07 | 14.2857
2022-02-08 | 9.93 | 2022-02-08 | -1.3334e-10
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-02-01 | 100 | 2022-02-01 | 100
2022-02-02 | 76.1429 | 2022-02-02 | 85.7143
2022-02-03 | 56.8571 | 2022-02-03 | 71.4286
2022-02-04 | 41.4286 | 2022-02-04 | 57.1429
2022-02-05 | 20 | 2022-02-05 | 42.8571
2022-02-06 | 20 | 2022-02-06 | 28.5714
2022-02-07 | 2.1429 | 2022-02-07 | 14.2857
2022-02-08 | 2.14 | 2022-02-08 | -1.3334e-10
Long
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-02-01 | 100 | 2022-02-01 | 100
2022-02-02 | 79.1667 | 2022-02-02 | 85.7143
2022-02-03 | 62.5 | 2022-02-03 | 71.4286
2022-02-04 | 41.6667 | 2022-02-04 | 57.1429
2022-02-05 | 25 | 2022-02-05 | 42.8571
2022-02-06 | 20 | 2022-02-06 | 28.5714
2022-02-07 | 5.6667 | 2022-02-07 | 14.2857
2022-02-08 | 5.6667 | 2022-02-08 | -1.3334e-10

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | -30.303
3 | 34.38 | 36 | -4.5
4 | 71.7 | 42 | 70.7143
5 | 52.02 | 53 | -1.8491
6 | 274.11 | 255 | 7.4941
7 | 39 | 72 | -45.8333
8 | 36 | 47 | -23.4043
9
10
11
Gideon
Sprint | Velocity | Capacity | % Error
2 | 8 | 7 | 14.2857
3 | 8 | 8 | 0
4 | 17.48 | 12 | 45.6667
5 | 13.23 | 13 | 1.7692
6 | 64 | 55 | 16.3636
7 | 13.33 | 15 | -11.1333
8 | 6.07 | 7 | -13.2857
9
10
11
Raymond
Sprint | Velocity | Capacity | % Error
2 | 2.33 | 7 | -66.7143
3 | 5.67 | 6 | -5.5
4 | 17.5 | 11 | 59.0909
5 | 13.5 | 12 | 12.5
6 | 57 | 55 | 3.6364
7 | 13.3 | 15 | -11.3333
8 | 6 | 7 | -0.14286
9
10
11
Brent
Sprint | Velocity | Capacity | % Error
2 | 6.33 | 8 | -20.875
3 | 8.02 | 8 | 0.25
4 | 17.58 | 12 | 46.5
5 | 11.37 | 12 | -5.25
6 | 63.73 | 55 | 15.8727
7 | 13.33 | 15 | -11.1333
8 | 6.85 | 7 | -2.1429
9
10
11
Vivian
Sprint | Velocity | Capacity | % Error
2 | 0 | 0 | 0
3 | 7.02 | 6 | 17
4 | 9.16 | 8 | 14.5
5 | 6.45 | 8 | -19.375
6 | 39.89 | 40 | -0.275
7 | 11.07 | 12 | -7.75
8 | 6.38 | 7 | -8.8571
9
10
11
Joshua
Sprint | Velocity | Capacity | % Error
2 | 6.33 | 8 | -20.875
3 | 5.66 | 6 | -5.6667
4 | 11.92 | 12 | -0.66667
5 | 7.58 | 8 | -5.25
6 | 49.43 | 50 | -1.14
7 | 13.72 | 15 | -8.5333
8 | 6.08 | 6 | 1.3333
9
10
11
Long
Sprint | Velocity | Capacity | % Error
8 | 6.3 | 6 | 5
9 |  |  | #DIV/0!
10 |  |  | #DIV/0!
11 |  |  | #DIV/0!
12 |  |  | #DIV/0!
13 |  |  | #DIV/0!
14 |  |  | #DIV/0!
15 |  |  | #DIV/0!
16 |  |  | #DIV/0!

## Sprint Planning
Sprint 8 Duration Cycle: 7 days
Sprint 8 Dates: 02/02/2022 - 02/08/2022
Name | Capacity (hours) | Events
Joshua | 6 | 2/8: Birthday Celebration @ Night
Raymond | 7 | Friday: 10am-12pm Staff Meeting Friday: 3:30pm-5:30pm Staff Meeting
Gideon | 7 | All of February. Black history month
Brent | 7 | 2/3: Roommate moving in
Long | 6
Vivian | 7
Total Capacity (Before Task Breakdown) | 40
Total Capacity (After Task Breakdown) | 36
Priorities
Project Plan
Test Plan
BRD
Web Based Photo Editing DAR

## Sprint Backlog
| Tasks | Estimated Effort Points (hrs) | Actual Effort Points (hrs) | Assignee | Start Date | End Date
Project Plan |  |  |  | Josh
| Revision: Identify human resources and their associated costs | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Revision: Provide a mitigation threshold for each risk to determine when risk will impact project schedule | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Revision: Provide the total estimate for the project | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Revision: Re-evaluate the time needed to deploy the solution to the production environment by not specifying a stand-alone work item within a Sprint | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Revision: Include work items for the setup of the production environment | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Revision: Identify the date the production deployment will take place | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Revision: Align the specific test cases to the planned Sprints | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
Test Plan |  |  |  | Long
| Determine the test creation time, test execution time, total testing time, and preconditions for "Photo editing" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Describe methods of integration testing for the "Photo editing" feature | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Describe methods of end-to-end testing for the "Photo editing" feature | 2 | 2 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Determine the test creation time, test execution time, total testing time, and preconditions for "Event Calendar" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Describe methods of integration testing for the "Event Calendar" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Describe methods of end-to-end testing for the "Event Calendar" feature | 2 | 2 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
BRD |  |  |  | Gideon
| Research API to use for "Photo Editing" feature | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Discuss and add "Photo editing" feature to the project | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Discuss and add "Calendar" feature to the project | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond | 2021-02-02 | 2021-02-07
| Determine functional requirements for the "Photo Editing" feature | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond |  | 2021-02-07
| Determine non-functional requirements for the "Photo Editing" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond |  | 2021-02-07
| Determine pass/fail requirements for the "Photo Editing" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond |  | 2021-02-07
| Determine functional requirements for the "Event Calendar" feature | 2 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond |  | 2021-02-07
| Determine non-functional requirements for the "Event Calendar" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond |  | 2021-02-07
| Determine pass/fail requirements for the "Event Calendar" feature | 1 | 1 | Josh, Gideon, Brent, Long, Vivian, Raymond |  | 2021-02-07
Web Based Photo Editing DAR |  |  |  | Vivian
| Research Pixo Rest API | 2 | 2 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
| Research Pho.to API | 2 | 2 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
| Research Img.ly API | 1 | 2 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
| Determine metrics for each technology | 1 | 2 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
| Rate each technology | 1 | 1 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
| Write conclusion | 2 | 2 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
| Benchmark Testing | 1 | 1 | Vivian, Josh, Raymond, Gideon | 2021-02-02 | 2021-02-07
|  | 47 | 36

## Project Backlog
Name | Priority | Internal Due Date | Client Due Date
Project Proposal/App-Specific Features | 1 | 2021-10-02 | 2021-09-06
Tech Spec | 1 | 2021-10-05 | 2021-10-06
Site Map | 2 | 2021-10-03 | 2021-10-06
BRD | 3 | 2021-10-05 | 2021-10-06
HLD | 4 | 2021-10-05 | 2021-10-06
Test Plan | 1 | 2021-10-23 | 2021-10-27
ProjectPlan | 2 | 2021-10-20 | 2021-10-27
Network Diagram | 3 | 2021-10-17 | 2021-10-27
Milestone 1 Revisions | 1 | 2021-11-08 | 2021-12-08
Tech Approval | 1 | 2021-11-16 | 2021-12-08
LLD Logging | 1 | 2021-11-24 | 2021-12-08
LLD User Management: Single Operation | 2 | 2021-11-24 | 2021-12-08
LLD User Management: Bulk Operation | 1 | 2021-12-02 | 2021-12-08
LLD Archiving | 2 | 2021-12-02 | 2021-12-08
Logging Implementation | 1 | 2021-12-14 | 2021-12-08
Archiving Implementation | 2 | 2021-12-14 | 2021-12-08
User Management Implementation | 3 | 2021-12-14 | 2021-12-08
DAR: Automated Testing | 4 | 2021-12-10 | 2021-12-08
DAR: Front-End Framework | 1 | 2022-01-30 | 2022-01-30
DAR: Weather API | 2 | 2022-01-30 | 2022-01-30
DAR: Data Store | 3 | 2022-01-30 | 2022-01-30
Revise Project Plan | 1 | 2022-02-04 | 2022-02-05
Revise Test Plan | 2 | 2022-02-04 | 2022-02-05
Revise BRD | 3 | 2022-02-04 | 2022-02-05
DAR: Web Based Photo Editing | 4 | 2022-02-04 | 2022-02-05
Set up AWS Server | 1 | 2022-02-11 | 2022-03-09
Set up AWS Database | 2 | 2022-02-11 | 2022-03-09
Set up AWS Networking | 3 | 2022-02-11 | 2022-03-09
LLD Authentication | 1 | 2022-02-16 | 2022-03-09
LLD Authorization | 2 | 2022-02-16 | 2022-03-09
LLD Account Creation (Registration) | 1 | 2022-02-16 | 2022-03-09
Authentication Implementation | 2 | 2022-02-24 | 2022-03-09
Authorization Implementation | 3 | 2022-02-16 | 2022-03-09
Account Creation (Registration) Implementation | 4 | 2022-02-16 | 2022-03-09
LLD Login/Logout | 5 | 2022-02-24 | 2022-03-09
LLD Account Deletion | 6 | 2022-02-24 | 2022-03-09
LLD Usage Analysis Dashboard | 7 | 2022-02-24 | 2022-03-09
Login/Logout Implementation | 8 | 2022-03-04 | 2022-03-09
Account Deletion Implementation | 9 | 2022-03-04 | 2022-03-09
Usage Analysis Dashboard Implementation | 10 | 2022-03-04 | 2022-03-09
Documentation | 11 | 2022-03-11 | 2022-03-09
Suggestions | 12 | 2022-03-19 | 2022-04-18
User Profile Dashboard | 13 | 2022-03-19 | 2022-04-18
Hyperlink Sharing | 14 | 2022-03-27 | 2022-04-18
Rating System | 15 | 2022-03-27 | 2022-04-18
Localized Weather Forecast | 16 | 2022-04-04 | 2022-04-18
Memory Album | 17 | 2022-04-04 | 2022-04-18
Duplicating Itineraries | 18 | 2022-04-04 | 2022-04-18