## Burndown Chart
Team
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-01-23 | 100 | 2022-01-23 | 100
2022-01-24 | 89.7436 | 2022-01-24 | 85.7143
2022-01-25 | 74.359 | 2022-01-25 | 71.4286
2022-01-26 | 58.9744 | 2022-01-26 | 57.1429
2022-01-27 | 43.5897 | 2022-01-27 | 42.8571
2022-01-28 | 28.2051 | 2022-01-28 | 28.5714
2022-01-29 | 15.3846 | 2022-01-29 | 14.2857
2022-01-30 | 2.5641 | 2022-01-30 | -1.3334e-10
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-01-23 | 100 | 2022-01-23 | 100
2022-01-24 | 84.3333 | 2022-01-24 | 85.7143
2022-01-25 | 77.6667 | 2022-01-25 | 71.4286
2022-01-26 | 72.1333 | 2022-01-26 | 57.1429
2022-01-27 | 52.1333 | 2022-01-27 | 42.8571
2022-01-28 | 32.1333 | 2022-01-28 | 28.5714
2022-01-29 | 32.1333 | 2022-01-29 | 14.2857
2022-01-30 | 8.8 | 2022-01-30 | -1.3334e-10
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-01-23 | 100 | 2022-01-23 | 100
2022-01-24 | 92.2667 | 2022-01-24 | 85.7143
2022-01-25 | 86.7133 | 2022-01-25 | 71.4286
2022-01-26 | 81.18 | 2022-01-26 | 57.1429
2022-01-27 | 61.18 | 2022-01-27 | 42.8571
2022-01-28 | 41.18 | 2022-01-28 | 28.5714
2022-01-29 | 32.13 | 2022-01-29 | 14.2857
2022-01-30 | 2.13 | 2022-01-30 | -1.3334e-10
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-01-23 | 100 | 2022-01-23 | 100
2022-01-24 | 84.3333 | 2022-01-24 | 85.7143
2022-01-25 | 77.6667 | 2022-01-25 | 71.4286
2022-01-26 | 72.1333 | 2022-01-26 | 57.1429
2022-01-27 | 52.1333 | 2022-01-27 | 42.8571
2022-01-28 | 32.1333 | 2022-01-28 | 28.5714
2022-01-29 | 32.13 | 2022-01-29 | 14.2857
2022-01-30 | 8.5967 | 2022-01-30 | -1.3334e-10
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-01-23 | 100 | 2022-01-23 | 100
2022-01-24 | 89.59 | 2022-01-24 | 85.7143
2022-01-25 | 78.29 | 2022-01-25 | 71.4286
2022-01-26 | 78.29 | 2022-01-26 | 57.1429
2022-01-27 | 53.29 | 2022-01-27 | 42.8571
2022-01-28 | 36.63 | 2022-01-28 | 28.5714
2022-01-29 | 36.63 | 2022-01-29 | 14.2857
2022-01-30 | 7.47 | 2022-01-30 | -1.3334e-10
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2022-01-23 | 100 | 2022-01-23 | 100
2022-01-24 | 84.3333 | 2022-01-24 | 85.7143
2022-01-25 | 68.6667 | 2022-01-25 | 71.4286
2022-01-26 | 62 | 2022-01-26 | 57.1429
2022-01-27 | 56.4667 | 2022-01-27 | 42.8571
2022-01-28 | 36.4667 | 2022-01-28 | 28.5714
2022-01-29 | 36.47 | 2022-01-29 | 14.2857
2022-01-30 | 6.47 | 2022-01-30 | -1.3334e-10

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | -30.303
3 | 34.38 | 36 | -4.5
4 | 71.7 | 42 | 70.7143
5 | 52.02 | 53 | -1.8491
6 | 274.11 | 255 | 7.4941
7 | 39 | 72 | -45.8333
8
9
10
11
Gideon
Sprint | Velocity | Capacity | % Error
2 | 8 | 7 | 14.2857
3 | 8 | 8 | 0
4 | 17.48 | 12 | 45.6667
5 | 13.23 | 13 | 1.7692
6 | 64 | 55 | 16.3636
7 | 13.33 | 15 | -11.1333
8
9
10
11
Raymond
Sprint | Velocity | Capacity | % Error
2 | 2.33 | 7 | -66.7143
3 | 5.67 | 6 | -5.5
4 | 17.5 | 11 | 59.0909
5 | 13.5 | 12 | 12.5
6 | 57 | 55 | 3.6364
7 | 13.3 | 15 | -11.3333
8
9
10
11
Brent
Sprint | Velocity | Capacity | % Error
2 | 6.33 | 8 | -20.875
3 | 8.02 | 8 | 0.25
4 | 17.58 | 12 | 46.5
5 | 11.37 | 12 | -5.25
6 | 63.73 | 55 | 15.8727
7 | 13.33 | 15 | -11.1333
8
9
10
11
Vivian
Sprint | Velocity | Capacity | % Error
2 | 0 | 0 | 0
3 | 7.02 | 6 | 17
4 | 9.16 | 8 | 14.5
5 | 6.45 | 8 | -19.375
6 | 39.89 | 40 | -0.275
7 | 11.07 | 12 | -7.75
8
9
10
11
Joshua
Sprint | Velocity | Capacity | % Error
2 | 6.33 | 8 | -20.875
3 | 5.66 | 6 | -5.6667
4 | 11.92 | 12 | -0.66667
5 | 7.58 | 8 | -5.25
6 | 49.43 | 50 | -1.14
7 | 13.72 | 15 | -8.5333
8
9
10
11

## Sprint Planning
Sprint 7 Duration Cycle: 7 days
Sprint 7 Dates: 1/24/22 - 1/30/22
Name | Capacity (hours) | Events
Joshua | 15
Raymond | 15 | January 24th: 1pm - 4pm: shift January 25th 6pm - January 26th 8am: Shift
Gideon | 15
Brent | 15
Vivian | 12 | Jan 29: Driving down to Long Beach
Total Capacity (Before Task Breakdown) | 72
Total Capacity (After Task Breakdown) | 39
Priorities

## Sprint Backlog
| Tasks | Estimated Effort Points (hrs) | Actual Effort Points (hrs) | Assignee | Start Date | End Date
DAR: Data Store |  |  |  | Joshua
| Revise DAR | 1 | 1 | Raymond, Joshua | 2022-01-29 | 2022-01-29
DAR: Front End Framework |  |  |  | Raymond
| Research React API | 2 | 2 | Brent, Raymond | 2022-01-25 | 2022-01-25
| Research Vue.js API | 2 | 2 | Brent, Raymond | 2022-01-26 | 2022-01-26
| Research Angular API | 2 | 2 | Brent, Raymond | 2022-01-27 | 2022-01-27
| Determine the metrics for each technology | 2 | 2 | Brent, Raymond | 2022-01-28 | 2022-01-28
| Run tests for memory allocation | 2 | 2 | Brent, Raymond | 2022-01-28 | 2022-01-28
| Concluding remarks | 2 | 2 | Brent, Raymond | 2022-01-30 | 2022-01-30
12
DAR: Weather API |  |  |  | Joshua
| Research Open Weather Map API | 2 | 2 | Joshua, Vivian | 2022-01-24 | 2022-01-24
| Research Tomorrow.io API | 2 | 2 | Joshua, Vivian | 2022-01-25 | 2022-01-25
| Research Weather API | 2 | 2 | Joshua, Vivian | 2022-01-26 | 2022-01-26
| Determine metrics for each technology | 2 | 2 | Joshua, Vivian | 2022-01-27 | 2022-01-27
| Rate each technology | 2 | 2 | Joshua, Vivian | 2022-01-28 | 2022-01-28
| Write conclusion | 1 | 1 | Joshua, Vivian | 2022-01-29 | 2022-01-29
| Benchmark Testing | 2 | 2 | Joshua, Vivian | 2022-01-30 | 2022-01-30
13
DAR: API Testing |  |  |  | Gideon
| Research: Postman, Insomnia, Paw | 2 | 2 | Gideon | 2022-01-24 | 2022-01-24
| Research: Authentication | 2 | 2 | Gideon | 2022-01-25 | 2022-01-25
| Research: Testing | 2 | 2 | Gideon | 2022-01-26 | 2022-01-26
| Research: Environment | 2 | 2 | Gideon | 2022-01-27 | 2022-01-27
| Research: Pricing | 2 | 2 | Gideon | 2022-01-28 | 2022-01-28
| Determine Metrics for DAR | 2 | 2 | Gideon | 2022-01-29 | 2022-01-29
| Write a conclusion | 1 | 1 | Gideon | 2022-01-30 | 2022-01-30
|  | 64 | 39
LLD for Authentication |  |  |  | Brent
| Success case #1: User submits valid security credentials. The user is automatically navigated to the user’s home view. | 2 |  | Brent, Vivian | 2022-01-24 | 2022-01-25
| Failure cases #1:User submits valid security credentials. Automatic navigation does not take place. | 2 |  | Brent, Vivian | 2022-01-26 | 2022-01-26
| Failure cases #2:User submits valid security credentials. The user is automatically navigated to a view other than the user’s home view. | 2 |  | Brent, Vivian | 2022-01-27 | 2022-01-27
| Failure cases #3:User submits invalid username. A system message displays “Invalid username or password provided. Retry again or contact system administrator”. | 2 |  | Brent, Vivian | 2022-01-28 | 2022-01-28
| Failure cases #4: User submits invalid OTP. A system message displays “Invalid username or password provided. Retry again or contact system administrator if issue persists”. | 2 |  | Brent, Vivian | 2022-01-29 | 2022-01-29
| Failure cases #5: User submits invalid security credentials. A system message displays “Invalid username or password provided. Retry again or contact system admin”. | 2 |  | Brent, Vivian | 2022-01-29 | 2022-01-29
| Failure cases #6:User submits valid security credentials for a disabled account. A system message displays “Account disabled. Perform account recovery or contact system admin”. The failure attempt is recorded accurately. | 2 |  | Brent, Vivian | 2022-01-30 | 2022-01-30
| Failure cases #7: User submits valid security credentials for a disabled account. A system message displays “Account disabled. Perform account recovery or contact system admin”. The failure attempt is recorded accurately. | 2 |  | Brent, Vivian | 2022-01-30 | 2022-01-30
LLD for Authorization |  |  |  | Gideon
| Success case #1: User attempts to access a protected functionality within authorization scope. Access is granted to perform functionality. | 2 |  | Gideon, Joshua | 2022-01-24 | 2022-01-24
| Success case #2: User attempts to access protected data within authorization scope. Access is granted to perform read operations. | 2 |  | Gideon, Joshua | 2022-01-24 | 2022-01-24
| Success case #3: User attempts to modify protected data within authorization scope. Access is granted to perform write operations. | 2 |  | Gideon, Joshua | 2022-01-25 | 2022-01-25
| Success case #4: User attempts to access protected views within authorization scope. | 2 |  | Gideon, Joshua | 2022-01-25 | 2022-01-25
| Failure case #1: Unauthorized access is not recorded by system when authorization fails. A system log of failure is attempted. | 2 |  | Gideon, Joshua | 2022-01-26 | 2022-01-26
| Failure case #2: User attempts to access a protected functionality outside of authorization scope. Access is denied and a system message displays “Unauthorized access”. | 2 |  | Gideon, Joshua | 2022-01-26 | 2022-01-26
| Failure case #3: User attempts to access protected data outside of authorization scope. Access is denied and a system message displays “Unauthorized access to data”. | 2 |  | Gideon, Joshua | 2022-01-27 | 2022-01-27
| Failure case #4: User attempts to modify protected data outside of authorization scope. Access is denied and a system message displays “Unauthorized access to data”. | 2 |  | Gideon, Joshua | 2022-01-28 | 2022-01-28
| Failure case #5: User attempts to access protected views outside of authorization scope. Access is denied and a system message displays “Unauthorized access to view”. | 2 |  | Gideon, Joshua | 2022-01-29 | 2022-01-29
| Failure case #6: User attempts to access protected views within authorization scope, but contains protected data that is not within read scope. Access is granted to the view. Upon completion of automatic navigation to view, a system message displays “Unauthorized access to data” with protected data not visible within the view. | 2 |  | Gideon, Joshua | 2022-01-29 | 2022-01-29
| Failure case #7: User attempts to access protected views within authorization scope, but contains protected data that is not within write scope. Access is granted to the view. Upon completion of automatic navigation to view, protected data is visible within the view. Attempts to modify the data will result in a system message that displays “Unauthorized access to data” | 2 |  | Gideon, Joshua | 2022-01-30 | 2022-01-30
LLD for Logout & Login |  |  |  | Raymond
| Success Case 1. User performs logout request. The active session ends. The user is automatically navigated to the default home view of the system with the default culture settings. A system message displays “Logout successfully” upon completion of automatic navigation to home view. The logout process completes within 5 seconds upon invocation. | 2 |  | Raymond | 2022-01-24 | 2022-01-24
| Failure Cases 1. User performs logout request. The active session has ended. The user is not automatically navigated to the default home view. A system message displays “Logout operation error” or no message is shown | 2 |  | Raymond | 2022-01-25 | 2022-01-25
| 2. User performs logout request. The active session has ended. The user is automatically navigated to the default home view, but not set to the default culture settings. A system message displays “Logout operation error” or no message is shown | 2 |  | Raymond | 2022-01-26 | 2022-01-26
| 3. The logout process takes longer than 5 seconds. | 2 |  | Raymond | 2022-01-27 | 2022-01-27
46

## Project Backlog
Name | Priority | Internal Due Date | Client Due Date
Project Proposal/App-Specific Features | 1 | 2021-10-02 | 2021-09-06
Tech Spec | 1 | 2021-10-05 | 2021-10-06
Site Map | 2 | 2021-10-03 | 2021-10-06
BRD | 3 | 2021-10-05 | 2021-10-06
HLD | 4 | 2021-10-05 | 2021-10-06
Test Plan | 1 | 2021-10-23 | 2021-10-27
ProjectPlan | 2 | 2021-10-20 | 2021-10-27
Network Diagram | 3 | 2021-10-17 | 2021-10-27
Milestone 1 Revisions | 1 | 2021-11-08 | 2021-12-08
Tech Approval | 1 | 2021-11-16 | 2021-12-08
LLD Logging | 1 | 2021-11-24 | 2021-12-08
LLD User Management: Single Operation | 2 | 2021-11-24 | 2021-12-08
LLD User Management: Bulk Operation | 1 | 2021-12-02 | 2021-12-08
LLD Archiving | 2 | 2021-12-02 | 2021-12-08
Logging Implementation | 1 | 2021-12-14 | 2021-12-08
Archiving Implementation | 2 | 2021-12-14 | 2021-12-08
User Management Implementation | 3 | 2021-12-14 | 2021-12-08
DAR: Automated Testing | 4 | 2021-12-10 | 2021-12-08
Data Store Access | 1 | 2022-02-06 | 2022-02-06
Documentation | 2 | 2022-02-06 | 2022-02-06
Set up AWS | 3 | 2022-02-06 | 2022-02-06
Suggestions | 4 | 2022-02-06 | 2022-02-06
User Profile Dashboard | 5 | 2022-02-06 | 2022-02-06
Registration | 6 | 2022-04-07 | 2022-04-07
Login/Logout | 7 | 2022-04-07 | 2022-04-07
Error Handling | 8 | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 9 | 2022-04-07 | 2022-04-07
Rating System | 10 | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 11 | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 12 | 2022-04-22 | 2022-04-22
User Access Control | 13 | 2022-04-22 | 2022-04-22
Memory Album | 14 | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 15 | 2022-04-22 | 2022-04-22