## Burndown Chart
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-09-22 | 100 | 2021-09-22 | 100
2021-09-23 | 99.5 | 2021-09-23 | 99
2021-09-24 | 99 | 2021-09-24 | 98.6
2021-09-25 | 98.6 | 2021-09-25 | 98
2021-09-26 | 98.6 | 2021-09-26 | 98
2021-09-27 | 98 | 2021-09-27 | 97.1
2021-09-28 | 97.6 | 2021-09-28 | 96.4
2021-09-29 | 97.2 | 2021-09-29 | 96
2021-09-30 | 97 | 2021-09-30 | 95.5
2021-10-01 | 96.7 | 2021-10-01 | 95
2021-10-02 | 96.1 | 2021-10-02 | 94.3
2021-10-03 | 96.1 | 2021-10-03 | 94.3
2021-10-04 | 95 | 2021-10-04 | 93
2021-10-05 | 94 | 2021-10-05 | 92
2021-10-12 | 93.4 | 2021-10-12 | 91.6
2021-10-13 | 93 | 2021-10-13 | 91.2
2021-10-14 | 92.7 | 2021-10-14 | 90.8
2021-10-15 | 92.4 | 2021-10-15 | 90.5
2021-10-16 | 92 | 2021-10-16 | 90
2021-10-17 | 92 | 2021-10-17 | 90
2021-10-18 | 91.7 | 2021-10-18 | 89.6
2021-10-19 | 91.4 | 2021-10-19 | 89.2
2021-10-20 | 91 | 2021-10-20 | 88.8
2021-10-21 | 90.8 | 2021-10-21 | 88.4
2021-10-22 | 90.6 | 2021-10-22 | 88.1
2021-10-23 | 90 | 2021-10-23 | 87.4
2021-10-24 | 90 | 2021-10-24 | 87.4
2021-10-25 | 89.5 | 2021-10-25 | 86.5
2021-10-26 | 89 | 2021-10-26 | 86

## Task Breakdown
Project Breakdown | Tasks | Start Date | End Date
Project Plan | Risk management | 2021-10-12 | 2021-10-15
| Developer Timeline (Simplified) | 2021-10-15 | 2021-10-18
| Project Roadmap | 2021-10-19 | 2021-10-19
| Budget | 2021-10-23 | 2021-10-23
| Developer Timeline (Detailed) | 2021-10-17 | 2021-10-23
Test Plan | Test Scope | 2021-10-12 | 2021-10-12
| General Test Policy | 2021-10-12 | 2021-10-12
| Datastore Access | 2021-10-12 | 2021-10-12
| Logging/Archiving | 2021-10-12 | 2021-10-12
| Login | 2021-10-12 | 2021-10-18
| Logout | 2021-10-12 | 2021-10-18
| User Access Controls | 2021-10-13 | 2021-10-13
| User Management | 2021-10-13 | 2021-10-13
| Registration | 2021-10-14 | 2021-10-14
| Duplicating Itineraries | 2021-10-19 | 2021-10-19
| Usage Analysis Dashboard | 2021-10-19 | 2021-10-19
| Hyperlink Sharing | 2021-10-19 | 2021-10-19
| Localized Weather Forecast | 2021-10-19 | 2021-10-19
| Rating Systems | 2021-10-19 | 2021-10-19
| Memory Album | 2021-10-20 | 2021-10-20
| User Profile Dashboard | 2021-10-20 | 2021-10-22
| Suggestions | 2021-10-20 | 2021-10-23
Network Diagram Tasks | Research | 2021-10-12 | 2021-10-16
- Learn about DNS web servers
- Learn about firewalls & security for application
- Learn about HTTP protocol
| Planning Diagram | 2021-10-12 | 2021-10-18
| Creating Diagram | 2021-10-18 | 2021-10-25
| Creating Descriptions based on diagram | 2021-10-20 | 2021-10-25

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2
3
4
5
6
7
8
9
10
11

## Project Backlog
Name | Priority | Story Points | Client Due Date | Internal Due Date
Project Proposal/Product Name and Description | 1 | 1 hrs | 2021-09-06 | 2021-09-10
Project Proposal/App-Specific Features | 2 | 20 hrs | 2021-09-06 | 2021-10-02
Project Proposal/Target Audience | 3 | 1 hrs | 2021-09-06 | 2021-09-12
Project Proposal/Pain Point | 4 | 1 hrs | 2021-09-06 | 2021-09-13
Project Proposal/Product Value | 5 | 1 hrs | 2021-09-06 | 2021-09-15
Project Proposal/Product Vision | 6 | 1 hrs | 2021-09-06 | 2021-09-17
Project Proposal/Product Competitors | 7 | 2 hrs | 2021-09-06 | 2021-09-19
Project Proposal/Product Uniqueness | 8 | 2 hrs | 2021-09-06 | 2021-09-21
Project Proposal/Project Scope | 9 | 2 hrs | 2021-09-06 | 2021-09-28
Tech Spec/Purpose | 10 | 1 hrs | 2021-10-06 | 2021-09-23
Tech Spec/IDE | 11 | 2 hrs | 2021-10-06 | 2021-10-01
Tech Spec/Programming Languages | 12 | 3 hrs | 2021-10-06 | 2021-10-01
Tech Spec/Browser | 13 | 1 hrs | 2021-10-06 | 2021-10-01
Tech Spec/Web Server | 14 | 1 hrs | 2021-10-06 | 2021-10-01
Tech Spec/Database Management System | 15 | 2 hrs | 2021-10-06 | 2021-10-02
Tech Spec/Front End Languages | 16 | 1 hrs | 2021-10-06 | 2021-10-02
Tech Spec/Frameworks(Front/Back End) | 17 | 1 hrs | 2021-10-06 | 2021-10-02
Tech Spec/Version Control Repository | 18 | 3 hrs | 2021-10-06 | 2021-10-05
Tech Spec/Version Control | 19 | 1 hrs | 2021-10-06 | 2021-10-05
Tech Spec/Diagram/Modeling | 20 | 2 hrs | 2021-10-06 | 2021-10-05
Tech Spec/Security | 21 | 1 hrs | 2021-10-06 | 2021-10-05
Site Map/Homepage | 23 | 1 hrs | 2021-10-06 | 2021-09-22
Site Map/Itinerary Creation | 24 | 4 hrs | 2021-10-06 | 2021-09-23
Site Map/Event Details | 25 | 8 hrs | 2021-10-06 | 2021-09-26
Site Map/Account Settings | 26 | 10 hrs | 2021-10-06 | 2021-09-28
Site Map/User Profile Dashboard | 27 | 10 hrs | 2021-10-06 | 2021-09-30
Site Map/Sign-In/Create Account | 28 | 6 hrs | 2021-10-06 | 2021-10-03
BRD/Introduction | 29 | 2 hrs | 2021-10-06 | 2021-09-28
BRD/Core Feature Requirements | 30 | 15 hrs | 2021-10-06 | 2021-10-01
BRD/App-specific Requirements | 31 | 15 hrs | 2021-10-06 | 2021-10-05
BRD/Glossary | 32 | 1 hrs | 2021-10-06 | 2021-10-05
HLD/Purpose & Scope | 33 | 1 hrs | 2021-10-06 | 2021-09-24
HLD/Software Architecture Diagram | 34 | 8 hrs | 2021-10-06 | 2021-10-04
HLD/General Overview | 35 | 1 hrs | 2021-10-06 | 2021-09-24
HLD/Layer Descriptions | 36 | 6 hrs | 2021-10-06 | 2021-10-04
HLD/Architecture Advantages/Disadvantages | 37 | 1 hrs | 2021-10-06 | 2021-10-05
Test Plan/Test Scope | 38 | 1 hrs | 2021-10-27 | 2021-10-12
Test Plan/General Test Policy | 39 | 2 hrs | 2021-10-27 | 2021-10-12
Test Plan/Datastore Access | 40 | 2 hrs | 2021-10-27 | 2021-10-12
Test Plan/Logging/Archiving | 41 | 1 hrs | 2021-10-27 | 2021-10-12
Test Plan/Login | 42 | 2 hrs | 2021-10-27 | 2021-10-18
Test Plan/Logout | 43 | 2 hrs | 2021-10-27 | 2021-10-18
Test Plan/User Access Controls | 44 | 3 hrs | 2021-10-27 | 2021-10-13
Test Plan/User Management | 45 | 1 hrs | 2021-10-27 | 2021-10-13
Test Plan/Registration | 46 | 3 hrs | 2021-10-27 | 2021-10-14
Test Plan/Duplicating Itineraries | 47 | 1 hrs | 2021-10-27 | 2021-10-19
Test Plan/Usage Analysis Dashboard | 48 | 2 hrs | 2021-10-27 | 2021-10-19
Test Plan/Hyperlink Sharing | 49 | 1 hrs | 2021-10-27 | 2021-10-19
Test Plan/Localized Weather Forecast | 50 | 1 hrs | 2021-10-27 | 2021-10-19
Test Plan/Rating Systems | 51 | 2 hrs | 2021-10-27 | 2021-10-19
Test Plan/Memory Album | 52 | 3 hrs | 2021-10-27 | 2021-10-20
Test Plan/User Profile Dashboard | 53 | 3 hrs | 2021-10-27 | 2021-10-22
Test Plan/Suggestions | 54 | 2 hrs | 2021-10-27 | 2021-10-23
ProjectPlan/Risk management | 56 | 10 hrs | 2021-10-27 | 2021-10-13
ProjectPlan/Project Roadmap | 57 | 1 hrs | 2021-10-27 | 2021-10-16
ProjectPlan/Developer Timeline (Simplified) | 58 | 5 hrs | 2021-10-27 | 2021-10-16
ProjectPlan/Developer Timeline (Detailed) | 59 | 10 hrs | 2021-10-27 | 2021-10-18
ProjectPlan/Budget | 60 | 4 hrs | 2021-10-27 | 2021-10-20
Network Diagram/Gather sources | 61 | 3 hrs | 2021-10-27 | 2021-10-12
Network Diagram/Learn about IIS web servers | 62 | 2 hrs | 2021-10-27 | 2021-10-12
Network Diagram/Learn about firewalls & security | 63 | 2 hrs | 2021-10-27 | 2021-10-13
Network Diagram/Learn about HTTP protocol | 64 | 2 hrs | 2021-10-27 | 2021-10-13
Network Diagram/Planning out the layout | 65 | 4 hrs | 2021-10-27 | 2021-10-14
Network Diagram/Planning out the necessary compon. | 66 | 4 hrs | 2021-10-27 | 2021-10-14
Network Diagram/Construct the diagram | 67 | 2 hrs | 2021-10-27 | 2021-10-15
Network Diagram/Rough draft of the description | 68 | 5 hrs | 2021-10-27 | 2021-10-16
Network Diagram/Revisions | 69 | 2 hrs | 2021-10-27 | 2021-10-17
Network Diagram/Final draft of the description | 70 | 1 hrs | 2021-10-27 | 2021-10-17
Network Diagram/Holistic QA | 71 | 4 hrs | 2021-10-27 | 2021-10-17
Low-Level Design Document | 72 | 45 hrs | 2021-12-06 | 2021-12-06
User Management | 73 | 84 hrs | 2021-12-06 | 2021-12-06
Logging | 74 | 60 hrs | 2021-12-06 | 2021-12-06
Data Store Access | 75 | 45 hrs | 2022-02-06 | 2022-02-06
Documentation | 76 | 30 hrs | 2022-02-06 | 2022-02-06
Set up AWS | 77 | 10 hrs | 2022-02-06 | 2022-02-06
Suggestions | 78 | 85 hrs | 2022-02-06 | 2022-02-06
User Profile Dashboard | 79 | 60 hrs | 2022-02-06 | 2022-02-06
Registration | 80 | 30 hrs | 2022-04-07 | 2022-04-07
Login/Logout | 81 | 60 hrs | 2022-04-07 | 2022-04-07
Error Handling | 82 | 60 hrs | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 83 | 40 hrs | 2022-04-07 | 2022-04-07
Rating System | 84 | 50 hrs | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 85 | 50 hrs | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 86 | 30 hrs | 2022-04-22 | 2022-04-22
User Access Control | 87 | 60 hrs | 2022-04-22 | 2022-04-22
Memory Album | 88 | 40 hrs | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 89 | 30 hrs | 2022-04-22 | 2022-04-22