## Burndown Chart
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-01 | 100 | 2021-11-01 | 100
2021-11-02 | 94 | 2021-11-02 | 85.71
2021-11-03 | 85 | 2021-11-03 | 71.42
2021-11-04 | 79 | 2021-11-04 | 57.13
2021-11-05 | 73 | 2021-11-05 | 42.84
2021-11-06 | 59 | 2021-11-06 | 28.55
2021-11-07 | 52 | 2021-11-07 | 14.26
2021-11-08 | 41 | 2021-11-08 | 0
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-01 | 100 | 2021-11-01 | 100
2021-11-02 | 85.71 | 2021-11-02 | 85.71
2021-11-03 | 71.42 | 2021-11-03 | 71.42
2021-11-04 | 57.13 | 2021-11-04 | 57.13
2021-11-05 | 41.42 | 2021-11-05 | 42.84
2021-11-06 | 14.28 | 2021-11-06 | 28.55
2021-11-07 | 0 | 2021-11-07 | 14.26
2021-11-08 | -14.28 | 2021-11-08 | 0
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-01 | 100 | 2021-11-01 | 100
2021-11-02 | 100 | 2021-11-02 | 85.71
2021-11-03 | 100 | 2021-11-03 | 71.42
2021-11-04 | 100 | 2021-11-04 | 57.13
2021-11-05 | 100 | 2021-11-05 | 42.84
2021-11-06 | 50 | 2021-11-06 | 28.55
2021-11-07 | 50 | 2021-11-07 | 14.26
2021-11-08 | 0 | 2021-11-08 | 0
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-01 | 100 | 2021-11-01 | 100
2021-11-02 | 87.5 | 2021-11-02 | 85.71
2021-11-03 | 75 | 2021-11-03 | 71.42
2021-11-04 | 62.5 | 2021-11-04 | 57.13
2021-11-05 | 50 | 2021-11-05 | 42.84
2021-11-06 | 37.5 | 2021-11-06 | 28.55
2021-11-07 | 0 | 2021-11-07 | 14.26
2021-11-08 | 0 | 2021-11-08 | 0
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-01 | 100 | 2021-11-01 | 100
2021-11-02 | 100 | 2021-11-02 | 85.71
2021-11-03 | 100 | 2021-11-03 | 71.42
2021-11-04 | 100 | 2021-11-04 | 57.13
2021-11-05 | 100 | 2021-11-05 | 42.84
2021-11-06 | 100 | 2021-11-06 | 28.55
2021-11-07 | 100 | 2021-11-07 | 14.26
2021-11-08 | 100 | 2021-11-08 | 0
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-01 | 100 | 2021-11-01 | 100
2021-11-02 | 100 | 2021-11-02 | 85.71
2021-11-03 | 100 | 2021-11-03 | 71.42
2021-11-04 | 87.5 | 2021-11-04 | 57.13
2021-11-05 | 87.5 | 2021-11-05 | 42.84
2021-11-06 | 65 | 2021-11-06 | 28.55
2021-11-07 | 65 | 2021-11-07 | 14.26
2021-11-08 | 20.9 | 2021-11-08 | 0

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | 30.303
3
4
5
6
7
8
9
10
11

## Sprint Planning
Sprint 2 Duration Cycle: 1 week
Sprint 2 Dates: 11/02/21 - 11/08/21
Name | Capacity (hours) | Events
Joshua | 8 | N/A
Raymond | 7 | 1-1 Meeting: Tue. Nov 2, 10:00AM - 10:30AM On Call Work: Tue. Nov 2, 6:00 PM - 8:00 AM Work Shift: Wed. Nov 3, 8:00AM - 11:00AM Staff Meeting: Fri. Nov 5, 3:30PM - 5:30PM
Gideon | 7 | N/A
Brent | 8 | Moving: Thu. Nov 4, Morning - 7:00PM Moving: Fri. Nov 5, Morning - 5:00PM
Vivian | 8 | N/A
Total Capacity (Before Task Breakdown) | 31
Total Capacity (After Task Breakdown) | 33
Priorities
Tech Approval

## Sprint Backlog
| Tasks | Effort Points (hrs) | Assignee | Start Date | End Date
Milestone 1 Revisions |  |  | Gideon
| Update missing versions of specific technologies | 1 | Gideon | 2021-11-02 | 2021-11-02
| Update Tech Spec to remove DAR aspect | 1 | Gideon | 2021-11-03 | 2021-11-04
| Account for productivity tools | 1 | Gideon | 2021-11-04 | 2021-11-05
| Account for collaboration tools such as Google Docs, Zoom, Trello, etc. | 2 | Gideon | 2021-11-06 | 2021-11-06
| Account for differences between development, testing and production environments. | 2 | Gideon | 2021-11-07 | 2021-11-08
| Remove implementation details in BRD | 1 | Joshua, Raymond | 2021-11-02 | 2021-11-02
| Add NFR usability in BRD | 1 | Joshua, Raymond | 2021-11-03 | 2021-11-03
| Add NFR maintainability in BRD | 1 | Joshua, Raymond | 2021-11-04 | 2021-11-04
| Add NFR scalability in BRD | 1 | Joshua, Raymond | 2021-11-05 | 2021-11-05
| Add NFR security in BRD | 1 | Joshua, Raymond | 2021-11-06 | 2021-11-06
| Add other NFR aspects in BRD | 1 | Joshua, Raymond | 2021-11-07 | 2021-11-07
| Indicate applicable user roles (worker vs owner) and other dependencies | 2 | Joshua, Raymond | 2021-11-08 | 2021-11-08
| Overlapping lines reduces readability | 2 | Vivian, Brent | 2021-11-03 | 2021-11-03
| Document does not show which UI component will cause which interactions (e.g. navigation, view update, etc.) | 2 | Vivian | 2021-11-05 | 2021-11-05
| Document contains dead end views; views that do not have outgoing routes, especially for error views | 2 | Vivian | 2021-11-06 | 2021-11-06
| Document does not clearly identify the difference between workers versus owner roles such as which view is accessible by which role | 2 | Vivian | 2021-11-08 | 2021-11-08
| Present the agreed upon solution & remove alternatives | 1 | Brent | 2021-11-02 | 2021-11-02
| Address how we'll handle authorization (security) at the UI & Database level | 1 | Brent | 2021-11-02 | 2021-11-02
| Address logging in the backend entry point & database entry point | 1 | Brent | 2021-11-03 | 2021-11-03
| Research what a hardware design should look like | 1 | Brent | 2021-11-03 | 2021-11-03
| Find the different components needed for HW arch | 1 | Brent | 2021-11-06 | 2021-11-06
| Create the HW architecture | 1 | Brent | 2021-11-08 | 2021-11-08

## Project Backlog
Name | Priority | Client Due Date | Internal Due Date
Project Proposal/App-Specific Features | 1 | 2021-09-06 | 2021-10-02
Tech Spec | 1 | 2021-10-06 | 2021-10-05
Site Map | 2 | 2021-10-06 | 2021-10-03
BRD | 3 | 2021-10-06 | 2021-10-05
HLD | 4 | 2021-10-06 | 2021-10-05
Test Plan | 1 | 2021-10-27 | 2021-10-23
ProjectPlan | 2 | 2021-10-27 | 2021-10-20
Network Diagram | 3 | 2021-10-27 | 2021-10-17
Milestone 1 Revisions | 1 | 2021-12-06 | 2021-11-08
Tech Approval | 1 | 2021-12-06 | 2021-11-08
Low-Level Design Document | 2 | 2021-12-06 | 2021-12-06
User Management | 3 | 2021-12-06 | 2021-12-06
Logging | 4 | 2021-12-06 | 2021-12-06
Data Store Access | 5 | 2022-02-06 | 2022-02-06
Documentation | 6 | 2022-02-06 | 2022-02-06
Set up AWS | 7 | 2022-02-06 | 2022-02-06
Suggestions | 8 | 2022-02-06 | 2022-02-06
User Profile Dashboard | 9 | 2022-02-06 | 2022-02-06
Registration | 10 | 2022-04-07 | 2022-04-07
Login/Logout | 11 | 2022-04-07 | 2022-04-07
Error Handling | 12 | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 13 | 2022-04-07 | 2022-04-07
Rating System | 14 | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 15 | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 16 | 2022-04-22 | 2022-04-22
User Access Control | 17 | 2022-04-22 | 2022-04-22
Memory Album | 18 | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 19 | 2022-04-22 | 2022-04-22