## Burndown Chart
Team
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-09 | 100 | 2021-11-09 | 100
2021-11-10 | 64.6111 | 2021-11-10 | 85.71
2021-11-11 | 64.6111 | 2021-11-11 | 71.42
2021-11-12 | 39.6111 | 2021-11-12 | 57.13
2021-11-13 | 20.0833 | 2021-11-13 | 42.84
2021-11-14 | 17.3056 | 2021-11-14 | 28.55
2021-11-15 | 4.4722 | 2021-11-15 | 14.26
2021-11-16 | -3.44 | 2021-11-16 | 0
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-09 | 100 | 2021-11-09 | 100
2021-11-10 | 100 | 2021-11-10 | 85.71
2021-11-11 | 68.75 | 2021-11-11 | 71.42
2021-11-12 | 68.75 | 2021-11-12 | 57.13
2021-11-13 | 60 | 2021-11-13 | 42.84
2021-11-14 | 23.75 | 2021-11-14 | 28.55
2021-11-15 | 11.25 | 2021-11-15 | 14.26
2021-11-16 | 0 | 2021-11-16 | 0
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-09 | 100 | 2021-11-09 | 100
2021-11-10 | 45 | 2021-11-10 | 85.71
2021-11-11 | 45 | 2021-11-11 | 71.42
2021-11-12 | 30 | 2021-11-12 | 57.13
2021-11-13 | 30 | 2021-11-13 | 42.84
2021-11-14 | 30 | 2021-11-14 | 28.55
2021-11-15 | 15 | 2021-11-15 | 14.26
2021-11-16 | 0 | 2021-11-16 | 0
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-09 | 100 | 2021-11-09 | 100
2021-11-10 | 100 | 2021-11-10 | 85.71
2021-11-11 | 83.33 | 2021-11-11 | 71.42
2021-11-12 | 83.33 | 2021-11-12 | 57.13
2021-11-13 | 56.66 | 2021-11-13 | 42.84
2021-11-14 | 45.59 | 2021-11-14 | 28.55
2021-11-15 | 3.92 | 2021-11-15 | 14.26
2021-11-16 | 0 | 2021-11-16 | 0
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-09 | 100 | 2021-11-09 | 100
2021-11-10 | 100 | 2021-11-10 | 85.71
2021-11-11 | 68.1 | 2021-11-11 | 71.42
2021-11-12 | 68.1 | 2021-11-12 | 57.13
2021-11-13 | 32 | 2021-11-13 | 42.84
2021-11-14 | 32 | 2021-11-14 | 28.55
2021-11-15 | 9.3 | 2021-11-15 | 14.26
2021-11-16 | 0 | 2021-11-16 | 0
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-09 | 100 | 2021-11-09 | 100
2021-11-10 | 100 | 2021-11-10 | 85.71
2021-11-11 | 66.75 | 2021-11-11 | 71.42
2021-11-12 | 66.75 | 2021-11-12 | 57.13
2021-11-13 | 20.85 | 2021-11-13 | 42.84
2021-11-14 | 20.85 | 2021-11-14 | 28.55
2021-11-15 | 20.85 | 2021-11-15 | 14.26
2021-11-16 | 0 | 2021-11-16 | 0

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | 30.303
3 | 34.38 | 36 | 4.5
4
5
6
7
8
9
10
11

## Sprint Planning
Sprint 3 Duration Cycle: 1 week
Sprint 3 Dates: 11/09/21 - 11/15/21
Name | Capacity (hours) | Events
Joshua | 6 | Veterans Day: Thu. Nov 11, All Day
Raymond | 6 | Veterans Day: Thu. Nov 11, All Day
Gideon | 8 | Veterans Day: Thu. Nov 11, All Day
Brent | 8 | Veterans Day: Thu. Nov 11, All Day
Vivian | 6 | Veterans Day: Thu. Nov 11, All Day
Total Capacity (Before Task Breakdown) | 34
Total Capacity (After Task Breakdown) | 36
Priorities
Tech Approval
Low-Level Design Document

## Sprint Backlog
| Tasks | Effort Points (hrs) | Assignee | Start Date | End Date
Tech Approval |  |  | Gideon
| DAR AWS: Compare web server technologies for compute engine | 2 | Brent | 2021-11-10 | 2021-11-11
| DAR AWS: Compare web server technologies for availability | 2 | Raymond
| DAR AWS: Compare web server technologies for security | 2 | Raymond
| DAR AWS: Compare web server technologies for documentation | 2 | Vivian
| DAR AWS: Compare web server technologies for simplicity of deployment | 2 | Raymond
| DAR AWS: Compare web server technologies for scalability | 2 | Brent | 2021-11-12 | 2021-11-13
| DAR AWS: Compare web server technologies for pricing | 1 | Vivian
| DAR for AWS Services: Conclusion | 2 | Brent, Vivian, Raymond | 2021-11-14 | 2021-11-15
| DAR Data Store: Compare data technologies for Security | 2 | Joshua | 2021-11-10 | 2021-11-11
| DAR Data Store: Compare technologies for Availability | 2 | Joshua | 2021-11-11
| DAR Data Store: Compare technologies for Performance/Speed | 2 | Joshua | 2021-11-12 | 2021-11-13
| DAR Data Store: Compare technologies for Backup Retention | 2 | Gideon | 2021-11-10 | 2021-11-11
| DAR Data Store: Compare technologies for Scalability | 2 | Gideon | 2021-11-11 | 2021-11-12
| DAR Data Store: Compare technologies for Pricing | 1 | Gideon | 2021-11-12 | 2021-11-13
| DAR Data Store: Conclusion | 2 | Gideon, Josh | 2021-11-14 | 2021-11-15
| DAR Figma: Compare technologies for Comprehensiveness and multiplayer collaboration |  | Vivian | 2021-11-13 | 2021-11-14
| DAR Figma: Compare technologies for Organization and Version Control | 2 | Vivian
| DAR Figma: Compare technologies for Ease of Use and pricing | 1 | Vivian
| DAR Figma: Write conclusion to elaborate for top three metrics | 2 | Vivian
| DAR Figma: Edit and finalize conclusion | 1 | Brent, Gideon, Vivian
Low-Level Design Document |  |  | Raymond
| Watch YouTube video playlist on LL Design | 2 | All | 2021-11-13 | 2021-11-15

## Project Backlog
Name | Priority | Client Due Date | Internal Due Date
Project Proposal/App-Specific Features | 1 | 2021-09-06 | 2021-10-02
Tech Spec | 1 | 2021-10-06 | 2021-10-05
Site Map | 2 | 2021-10-06 | 2021-10-03
BRD | 3 | 2021-10-06 | 2021-10-05
HLD | 4 | 2021-10-06 | 2021-10-05
Test Plan | 1 | 2021-10-27 | 2021-10-23
ProjectPlan | 2 | 2021-10-27 | 2021-10-20
Network Diagram | 3 | 2021-10-27 | 2021-10-17
Milestone 1 Revisions | 1 | 2021-12-06 | 2021-11-08
Tech Approval | 1 | 2021-12-06 | 2021-11-16
Low-Level Design Document | 1 | 2021-12-06 | 2021-12-06
User Management | 2 | 2021-12-06 | 2021-12-06
Logging | 3 | 2021-12-06 | 2021-12-06
Data Store Access | 4 | 2022-02-06 | 2022-02-06
Documentation | 5 | 2022-02-06 | 2022-02-06
Set up AWS | 6 | 2022-02-06 | 2022-02-06
Suggestions | 7 | 2022-02-06 | 2022-02-06
User Profile Dashboard | 8 | 2022-02-06 | 2022-02-06
Registration | 9 | 2022-04-07 | 2022-04-07
Login/Logout | 10 | 2022-04-07 | 2022-04-07
Error Handling | 11 | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 12 | 2022-04-07 | 2022-04-07
Rating System | 13 | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 14 | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 15 | 2022-04-22 | 2022-04-22
User Access Control | 16 | 2022-04-22 | 2022-04-22
Memory Album | 17 | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 18 | 2022-04-22 | 2022-04-22