## Burndown Chart
Team
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 64.6111 | 2021-11-26 | 85.71
2021-11-27 | 64.6111 | 2021-11-27 | 71.42
2021-11-28 | 39.6111 | 2021-11-28 | 57.13
2021-11-29 | 20.0833 | 2021-11-29 | 42.84
2021-11-30 | 17.3056 | 2021-11-30 | 28.55
2021-12-01 | 4.4722 | 2021-12-01 | 14.26
2021-12-02 | -3.44 | 2021-12-02 | 0
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 100 | 2021-11-26 | 85.71
2021-11-27 | 68.75 | 2021-11-27 | 71.42
2021-11-28 | 68.75 | 2021-11-28 | 57.13
2021-11-29 | 60 | 2021-11-29 | 42.84
2021-11-30 | 23.75 | 2021-11-30 | 28.55
2021-12-01 | 11.25 | 2021-12-01 | 14.26
2021-12-02 | 0 | 2021-12-02 | 0
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 45 | 2021-11-26 | 85.71
2021-11-27 | 45 | 2021-11-27 | 71.42
2021-11-28 | 30 | 2021-11-28 | 57.13
2021-11-29 | 30 | 2021-11-29 | 42.84
2021-11-30 | 30 | 2021-11-30 | 28.55
2021-12-01 | 15 | 2021-12-01 | 14.26
2021-12-02 | 0 | 2021-12-02 | 0
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 100 | 2021-11-26 | 85.71
2021-11-27 | 83.33 | 2021-11-27 | 71.42
2021-11-28 | 83.33 | 2021-11-28 | 57.13
2021-11-29 | 56.66 | 2021-11-29 | 42.84
2021-11-30 | 45.59 | 2021-11-30 | 28.55
2021-12-01 | 3.92 | 2021-12-01 | 14.26
2021-12-02 | 0 | 2021-12-02 | 0
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 100 | 2021-11-26 | 85.71
2021-11-27 | 68.1 | 2021-11-27 | 71.42
2021-11-28 | 68.1 | 2021-11-28 | 57.13
2021-11-29 | 32 | 2021-11-29 | 42.84
2021-11-30 | 32 | 2021-11-30 | 28.55
2021-12-01 | 9.3 | 2021-12-01 | 14.26
2021-12-02 | 0 | 2021-12-02 | 0
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 100 | 2021-11-26 | 85.71
2021-11-27 | 66.75 | 2021-11-27 | 71.42
2021-11-28 | 66.75 | 2021-11-28 | 57.13
2021-11-29 | 20.85 | 2021-11-29 | 42.84
2021-11-30 | 20.85 | 2021-11-30 | 28.55
2021-12-01 | 20.85 | 2021-12-01 | 14.26
2021-12-02 | 0 | 2021-12-02 | 0

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | 30.303
3 | 34.38 | 36 | 4.5
4 | 71.7 | 42 | 70.7143
5
6
7
8
9
10
11

## Sprint Planning
Sprint 4 Duration Cycle: 1 week
Sprint 4 Dates: 11/18/21 - 11/24/21
Name |  | Events
Joshua | 12 | N/A
Raymond | 11 | November 19th 3:30pm - 5:30 pm Meeting November 23th: Driving home
Gideon | 12 | N/A
Brent | 12 | N/A
Vivian | 8 | November 19: Busy during day November 20: Driving back home all day
Total Capacity (Before Task Breakdown) | 55
Total Capacity (After Task Breakdown) | 42
Priorities
Low-Level Design Document

## Sprint Backlog
| Tasks | Estimated Effort Points (hrs) | Actual Effort Points (hrs) | Assignee | Start Date | End Date
LLD Logging |  |  |  | Gideon
| Watch YouTube video on Logging in .NET Core 3.0 https://www.youtube.com/watch?v=oXNslgIXIbQ | 1 | 1 | Raymond, Brent, Gideon | 2021-11-18 | 2021-11-19
| Research how logging works in .NET | 2 | 1.5 | Raymond, Brent, Gideon | 2021-11-19 | 2021-11-20
| Create sequence diagram for logging system success events | 2 | 2 | Raymond, Brent, Gideon | 2021-11-20 | 2021-11-21
| Create sequence diagram for logging system failure events | 2 | 2 | Raymond, Brent, Gideon | 2021-11-21 | 2021-11-21
| Create sequence diagram for logging user success events | 2 | 2 | Raymond, Brent, Gideon | 2021-11-22 | 2021-11-22
| Create sequence diagram for logging user failure events | 2 | 2 | Raymond, Brent, Gideon | 2021-11-22 | 2021-11-22
| Create sequence diagram for logging failure case 1: The logging process took longer than 5 seconds to complete upon invocation | 2 | 2 | Raymond, Brent, Gideon | 2021-11-23 | 2021-11-24
| Create sequence diagram for logging failure case 2: The logging process blocks a user from interacting with the system | 2 | 1.5 | Raymond, Brent, Gideon | 2021-11-23 | 2021-11-24
| Create sequence diagram for logging failure case 2: The logging process completes within 5 seconds, but did not save to a persistent date store | 2 | 2 | Raymond, Brent, Gideon | 2021-11-23 | 2021-11-24
| Create sequence diagram for logging failure case 4: The logging process completes with 5 seconds, but did not accurately save the event to the persistent data store | 2 | 2 | Raymond, Brent, Gideon | 2021-11-23 | 2021-11-24
| Create sequence diagram for logging failure case 5: Previously saved log entries are modifiable | 2 | 1.5 | Raymond, Brent, Gideon | 2021-11-23 | 2021-11-24
LLD User Management |  |  |  | Josh
| Create draft for User Management sequence diagram | 2 | 1 | Vivian, Josh | 2021-11-18 | 2021-11-18
| Create successful UM sequence diagram for Create Account | 2 | 1 | Vivian, Josh | 2021-11-20 | 2021-11-20
| Create Error Case Authorization for UM sequence diagrams | 2 | 1 | Vivian, Josh | 2021-11-20 | 2021-11-20
| Create Error Case Input Validation UM sequence diagrams | 2 | 1 | Vivian, Josh | 2021-11-20 | 2021-11-20
| Create successful UM sequence diagram for Update Account | 2 | 1 | Vivian, Josh | 2021-11-21 | 2021-11-21
| Create successful UM sequence diagram for Delete Account | 2 | 1 | Vivian, Josh | 2021-11-22 | 2021-11-22
| Create successful UM sequence diagram for Disable Account | 2 | 1 | Vivian, Josh | 2021-11-22 | 2021-11-22
| Create successful UM sequence diagram for Enable Account | 2 | 1 | Vivian, Josh | 2021-11-22 | 2021-11-22
| Create failure cases 1/3/5 for UM sequence diagram Create Account | 2 | 1 | Vivian, Josh | 2021-11-23 | 2021-11-23
| Create failure cases 1/3/5 for UM sequence diagram Update Account | 2 | 1 | Vivian, Josh | 2021-11-23 | 2021-11-23
| Create failure cases 1/3/5 for UM sequence diagram Delete Account | 2 | 1 | Vivian, Josh | 2021-11-23 | 2021-11-23
| Create failure cases 1/3/5 for UM sequence diagram Disable Account | 2 | 1 | Vivian, Josh | 2021-11-23 | 2021-11-23
| Create failure cases 1/3/5 for UM sequence diagram Disable Account | 2 | 1 | Vivian, Josh | 2021-11-23 | 2021-11-23
| HOURS TOTAL | 42

## Project Backlog
Name | Priority | Client Due Date | Internal Due Date
Project Proposal/App-Specific Features | 1 | 2021-09-06 | 2021-10-02
Tech Spec | 1 | 2021-10-06 | 2021-10-05
Site Map | 2 | 2021-10-06 | 2021-10-03
BRD | 3 | 2021-10-06 | 2021-10-05
HLD | 4 | 2021-10-06 | 2021-10-05
Test Plan | 1 | 2021-10-27 | 2021-10-23
ProjectPlan | 2 | 2021-10-27 | 2021-10-20
Network Diagram | 3 | 2021-10-27 | 2021-10-17
Milestone 1 Revisions | 1 | 2021-12-08 | 2021-11-08
Tech Approval | 1 | 2021-12-08 | 2021-11-16
LLD Logging | 1 | 2021-12-08 | 2021-11-24
LLD User Management: Single Operation | 2 | 2021-12-08 | 2021-11-24
LLD User Management: Bulk Operation | 1 | 2021-12-08 | 2021-12-06
LLD Archiving | 2 | 2021-12-08 | 2021-12-06
Logging Implementation | 3 | 2021-12-08 | 2021-12-06
User Management Implementation | 4 | 2021-12-08 | 2021-12-06
Archiving Implementation | 5 | 2021-12-08 | 2021-12-06
Data Store Access | 6 | 2022-02-06 | 2022-02-06
Documentation | 7 | 2022-02-06 | 2022-02-06
Set up AWS | 8 | 2022-02-06 | 2022-02-06
Suggestions | 9 | 2022-02-06 | 2022-02-06
User Profile Dashboard | 10 | 2022-02-06 | 2022-02-06
Registration | 11 | 2022-04-07 | 2022-04-07
Login/Logout | 12 | 2022-04-07 | 2022-04-07
Error Handling | 13 | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 14 | 2022-04-07 | 2022-04-07
Rating System | 15 | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 16 | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 17 | 2022-04-22 | 2022-04-22
User Access Control | 18 | 2022-04-22 | 2022-04-22
Memory Album | 19 | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 20 | 2022-04-22 | 2022-04-22