## Burndown Chart
Team
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 82.3636 | 2021-11-26 | 85.71
2021-11-27 | 74.9455 | 2021-11-27 | 71.42
2021-11-28 | 74.9455 | 2021-11-28 | 57.13
2021-11-29 | 54.9455 | 2021-11-29 | 42.84
2021-11-30 | 33.1273 | 2021-11-30 | 28.55
2021-12-01 | 21.6182 | 2021-12-01 | 14.26
2021-12-02 | 8.0727 | 2021-12-02 | 0
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 83.4615 | 2021-11-26 | 85.71
2021-11-27 | 75.7692 | 2021-11-27 | 71.42
2021-11-28 | 75.7692 | 2021-11-28 | 57.13
2021-11-29 | 52.6923 | 2021-11-29 | 42.84
2021-11-30 | 23.8462 | 2021-11-30 | 28.55
2021-12-01 | 16.1538 | 2021-12-01 | 14.26
2021-12-02 | -23.4615 | 2021-12-02 | 0
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 83.9167 | 2021-11-26 | 85.71
2021-11-27 | 75.5833 | 2021-11-27 | 71.42
2021-11-28 | 75.5833 | 2021-11-28 | 57.13
2021-11-29 | 50.5833 | 2021-11-29 | 42.84
2021-11-30 | 19.3333 | 2021-11-30 | 28.55
2021-12-01 | -0.083333 | 2021-12-01 | 14.26
2021-12-02 | -43 | 2021-12-02 | 0
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 73.9625 | 2021-11-26 | 85.71
2021-11-27 | 70.9615 | 2021-11-27 | 71.42
2021-11-28 | 70.96 | 2021-11-28 | 57.13
2021-11-29 | 63.2692 | 2021-11-29 | 42.84
2021-11-30 | 33.9423 | 2021-11-30 | 28.55
2021-12-01 | 11.3462 | 2021-12-01 | 14.26
2021-12-02 | 11.35 | 2021-12-02 | 0
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 74 | 2021-11-26 | 85.71
2021-11-27 | 61.5 | 2021-11-27 | 71.42
2021-11-28 | 61.5 | 2021-11-28 | 57.13
2021-11-29 | 49 | 2021-11-29 | 42.84
2021-11-30 | 30.25 | 2021-11-30 | 28.55
2021-12-01 | 30.25 | 2021-12-01 | 14.26
2021-12-02 | 19.83 | 2021-12-02 | 0
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-11-25 | 100 | 2021-11-25 | 100
2021-11-26 | 78.9167 | 2021-11-26 | 85.71
2021-11-27 | 70.5833 | 2021-11-27 | 71.42
2021-11-28 | 70.58 | 2021-11-28 | 57.13
2021-11-29 | 45.58 | 2021-11-29 | 42.84
2021-11-30 | 33.08 | 2021-11-30 | 28.55
2021-12-01 | 24.7467 | 2021-12-01 | 14.26
2021-12-02 | -18.17 | 2021-12-02 | 0

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | 30.303
3 | 34.38 | 36 | 4.5
4 | 71.7 | 42 | 70.7143
5 | 52.02 | 53 | 1.8491
6
7
8
9
10
11

## Sprint Planning
Sprint 5 Duration Cycle: 1 week
Sprint 5 Dates: 11/26/21 - 12/02/21
Name | Capacity (hours) | Events
Joshua | 8 | N/A
Raymond | 12 | 11/26/2021: driving back to LB
Gideon | 13 | 11/26 6:45 PM ~ 10 PM
Brent | 12 | November 30th - Exam for CECS 326
Vivian | 8 | November 28th - Need to drive back to Long Beach
Total Capacity (Before Task Breakdown) | 53
Total Capacity (After Task Breakdown) | 44
Priorities
LLD User Management: Bulk Operation
LLD Archiving
Logging Implementation
User Management Implementation
Archiving Implementation

## Sprint Backlog
| Tasks | Estimated Effort Points (hrs) | Actual Effort Points (hrs) | Assignee | Start Date | End Date
LLD Archiving |  |  |  | Gideon
| Creating sequence diagram draft for Archiving | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create success case for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create failure case 1 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create failure case 2 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create failure case 3 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create failure case 4 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create failure case 5 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-02
| Create failure case 6 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-03
| Create failure case 7 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-03
| Create failure case 8 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-03
| Create failure case 9 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-03
| Create failure case 10 for Archiving sequence diagram | 2 | 2 | Raymond, Brent, Gideon | 2021-11-26 | 2021-12-03
LLD User Management: Bulk Operation |  |  |  | Josh
| Create Success Case for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-26 | 2021-11-26
| Create Failure Case 2 for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-26 | 2021-11-26
| Create Failure Case 4 for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-26 | 2021-11-26
| Create Failure Case 6 for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-26 | 2021-11-26
| Create Failure Case 7 for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-27 | 2021-11-27
| Create Failure Case 8 for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-27 | 2021-11-27
| Create Failure Case 9 for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-27 | 2021-11-27
| Create Error Case Authentication for UM sequence diagram Bulk Operation | 1 | 2 | Vivian, Josh | 2021-11-27 | 2021-11-27
| Create Error Case Overloaded Request for UM sequence diagram Bulk Operation | 1 | 2 | Vivian | 2021-11-27 | 2021-11-27
| Create Error Case Oversized File Extract for UM sequence diagram Bulk Operation | 1 | 2 | Vivian | 2021-11-27 | 2021-11-27

## Project Backlog
Name | Priority | Client Due Date | Internal Due Date
Project Proposal/App-Specific Features | 1 | 2021-09-06 | 2021-10-02
Tech Spec | 1 | 2021-10-06 | 2021-10-05
Site Map | 2 | 2021-10-06 | 2021-10-03
BRD | 3 | 2021-10-06 | 2021-10-05
HLD | 4 | 2021-10-06 | 2021-10-05
Test Plan | 1 | 2021-10-27 | 2021-10-23
ProjectPlan | 2 | 2021-10-27 | 2021-10-20
Network Diagram | 3 | 2021-10-27 | 2021-10-17
Milestone 1 Revisions | 1 | 2021-12-08 | 2021-11-08
Tech Approval | 1 | 2021-12-08 | 2021-11-16
LLD Logging | 1 | 2021-12-08 | 2021-11-24
LLD User Management: Single Operation | 2 | 2021-12-08 | 2021-11-24
LLD User Management: Bulk Operation | 1 | 2021-12-08 | 2021-12-02
LLD Archiving | 2 | 2021-12-08 | 2021-12-02
Logging Implementation | 1 | 2021-12-08 | 2021-12-10
User Management Implementation | 2 | 2021-12-08 | 2021-12-10
Archiving Implementation | 3 | 2021-12-08 | 2021-12-10
DAR Modifications | 4 | 2021-12-08 | 2021-12-10
Data Store Access | 5 | 2022-02-06 | 2022-02-06
Documentation | 6 | 2022-02-06 | 2022-02-06
Set up AWS | 7 | 2022-02-06 | 2022-02-06
Suggestions | 8 | 2022-02-06 | 2022-02-06
User Profile Dashboard | 9 | 2022-02-06 | 2022-02-06
Registration | 10 | 2022-04-07 | 2022-04-07
Login/Logout | 11 | 2022-04-07 | 2022-04-07
Error Handling | 12 | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 13 | 2022-04-07 | 2022-04-07
Rating System | 14 | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 15 | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 16 | 2022-04-22 | 2022-04-22
User Access Control | 17 | 2022-04-22 | 2022-04-22
Memory Album | 18 | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 19 | 2022-04-22 | 2022-04-22