## Burndown Chart
Team
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-12-03 | 100 | 2021-12-03 | 100
2021-12-04 | 93.6508 | 2021-12-04 | 90.9091
2021-12-05 | 93.6508 | 2021-12-05 | 81.8182
2021-12-06 | 87.3016 | 2021-12-06 | 72.7273
2021-12-07 | 80.9524 | 2021-12-07 | 63.6364
2021-12-08 | 65.0794 | 2021-12-08 | 54.5455
2021-12-09 | 58.7302 | 2021-12-09 | 45.4545
2021-12-10 | 49.2063 | 2021-12-10 | 36.3636
2021-12-11 | 31.746 | 2021-12-11 | 27.2727
2021-12-12 | 23.8095 | 2021-12-12 | 18.1818
2021-12-13 | 10.3175 | 2021-12-13 | 9.0909
2021-12-14 | 0.79365 | 2021-12-14 | 0
Gideon
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-12-03 | 100 | 2021-12-03 | 100
2021-12-04 | 93.5455 | 2021-12-04 | 90.9091
2021-12-05 | 93.5455 | 2021-12-05 | 81.8182
2021-12-06 | 82.0545 | 2021-12-06 | 72.7273
2021-12-07 | 74.2727 | 2021-12-07 | 63.6364
2021-12-08 | 67 | 2021-12-08 | 54.5455
2021-12-09 | 60.5818 | 2021-12-09 | 45.4545
2021-12-10 | 42.2545 | 2021-12-10 | 36.3636
2021-12-11 | 29.0182 | 2021-12-11 | 27.2727
2021-12-12 | 8.1455 | 2021-12-12 | 18.1818
2021-12-13 | -7.6364 | 2021-12-13 | 9.0909
2021-12-14 | -16.8727 | 2021-12-14 | 0
Raymond
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-12-03 | 100 | 2021-12-03 | 100
2021-12-04 | 93.5455 | 2021-12-04 | 90.9091
2021-12-05 | 93.5455 | 2021-12-05 | 81.8182
2021-12-06 | 84.0727 | 2021-12-06 | 72.7273
2021-12-07 | 76.5091 | 2021-12-07 | 63.6364
2021-12-08 | 67.4182 | 2021-12-08 | 54.5455
2021-12-09 | 62.4909 | 2021-12-09 | 45.4545
2021-12-10 | 55.2182 | 2021-12-10 | 36.3636
2021-12-11 | 41.3455 | 2021-12-11 | 27.2727
2021-12-12 | 21.3455 | 2021-12-12 | 18.1818
2021-12-13 | 7.6 | 2021-12-13 | 9.0909
2021-12-14 | -1.6364 | 2021-12-14 | 0
Joshua
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-12-03 | 100 | 2021-12-03 | 100
2021-12-04 | 92.9 | 2021-12-04 | 90.9091
2021-12-05 | 92.9 | 2021-12-05 | 81.8182
2021-12-06 | 86.8 | 2021-12-06 | 72.7273
2021-12-07 | 83.14 | 2021-12-07 | 63.6364
2021-12-08 | 75.82 | 2021-12-08 | 54.5455
2021-12-09 | 69.22 | 2021-12-09 | 45.4545
2021-12-10 | 54.22 | 2021-12-10 | 36.3636
2021-12-11 | 44.72 | 2021-12-11 | 27.2727
2021-12-12 | 34.72 | 2021-12-12 | 18.1818
2021-12-13 | 20.82 | 2021-12-13 | 9.0909
2021-12-14 | 1.16 | 2021-12-14 | 0
Vivian
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-12-03 | 100 | 2021-12-03 | 100
2021-12-04 | 98.98 | 2021-12-04 | 90.9091
2021-12-05 | 98.975 | 2021-12-05 | 81.8182
2021-12-06 | 87.59 | 2021-12-06 | 72.7273
2021-12-07 | 82.23 | 2021-12-07 | 63.6364
2021-12-08 | 73.91 | 2021-12-08 | 54.5455
2021-12-09 | 66.62 | 2021-12-09 | 45.4545
2021-12-10 | 58.24 | 2021-12-10 | 36.3636
2021-12-11 | 48.91 | 2021-12-11 | 27.2727
2021-12-12 | 37.41 | 2021-12-12 | 18.1818
2021-12-13 | 15.129 | 2021-12-13 | 9.0909
2021-12-14 | 2.12 | 2021-12-14 | 0
Brent
Date | % Progress Remaining | Date | % Progress Remaining
| Actual Burndown |  | Expected Burndown
2021-12-03 | 100 | 2021-12-03 | 100
2021-12-04 | 91 | 2021-12-04 | 90.9091
2021-12-05 | 91 | 2021-12-05 | 81.8182
2021-12-06 | 74.6727 | 2021-12-06 | 72.7273
2021-12-07 | 67.0909 | 2021-12-07 | 63.6364
2021-12-08 | 58.5818 | 2021-12-08 | 54.5455
2021-12-09 | 52.9091 | 2021-12-09 | 45.4545
2021-12-10 | 37.4182 | 2021-12-10 | 36.3636
2021-12-11 | 26.3273 | 2021-12-11 | 27.2727
2021-12-12 | 9.5091 | 2021-12-12 | 18.1818
2021-12-13 | -6.2727 | 2021-12-13 | 9.0909
2021-12-14 | -15.8727 | 2021-12-14 | 0

## Percent Error
Sprint | Velocity | Capacity | % Error
0 | 108 | 84 | 28.5714
1 | 96 | 84 | 14.2857
2 | 23 | 33 | 30.303
3 | 34.38 | 36 | 4.5
4 | 71.7 | 42 | 70.7143
5 | 52.02 | 53 | 1.8491
6 | 274.11 | 255 | 7.4941
7
8
9
10
11

## Sprint Planning
Sprint 6 Duration Cycle: 11 days
Sprint 6 Dates: 12/4/21 - 12/14/21
Name | Capacity (hours) | Events
Joshua | 50
Raymond | 55 | Tuesday: 10am 1:1 meeting with boss Tuesday 6pm - Wednesday 8am: on call shift Wednesday 8am - 11am shift
Gideon | 55 | Sat. 12/4
Brent | 55 | Friday (12/10): Eye exam at 9:20am
Vivian | 40 | Sunday: 4pm - Night celebrate dereks birthday with family
Total Capacity (Before Task Breakdown) | 255
Total Capacity (After Task Breakdown) | 252
Priorities
Logging Implementation
Archiving Implementation
User Management Implementation
DAR: Automated Testing

## Sprint Backlog
| Tasks | Estimated Effort Points (hrs) | Actual Effort Points (hrs) | Assignee | Start Date | End Date
Logging LLD(Redesign) |  |  |  | Gideon
| Redesign sequence diagram for logging system success events | 1 | 2 | Raymond,Brent,Gideon | 2021-12-04 | 2021-12-06
| Redesign sequence diagram for logging system failure events | 1 | 2 | Raymond,Brent,Gideon | 2021-12-04 | 2021-12-06
| Redesign sequence diagram for logging user success events | 1 | 2 | Raymond,Brent,Gideon | 2021-12-04 | 2021-12-06
| Redesign sequence diagram for logging user failure events | 1 | 2 | Raymond,Brent,Gideon | 2021-12-04 | 2021-12-04
2
| Redesign sequence diagram for logging failure case 1: The logging process took longer than 5 seconds to complete upon invocation | 1 | 2 | Raymond,Brent,Gideon | 2021-12-06 | 2021-12-06
| Redesign sequence diagram for logging failure case 2: The logging process blocks a user from interacting with the system | 1 | 2 | Raymond,Brent,Gideon | 2021-12-06 | 2021-12-06
| Redesign sequence diagram for logging failure case 2: The logging process completes within 5 seconds, but did not save to a persistent date store | 1 | 2 | Raymond,Brent,Gideon | 2021-12-06 | 2021-12-06
| Redesign sequence diagram for logging failure case 4: The logging process completes with 5 seconds, but did not accurately save the event to the persistent data store | 1 | 2 | Raymond,Brent,Gideon | 2021-12-07 | 2021-12-07
| Redesign sequence diagram for logging failure case 5: Previously saved log entries are modifiable | 1 | 2 | Raymond,Brent,Gideon | 2021-12-07 | 2021-12-07
|  | 9 | 20
Archiving LLD(Redesign) |  |  |  | Gideon
| Redesign failure case 1 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-07 | 2021-12-08
| Redesign failure case 2 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-07 | 2021-12-08
| Redesign failure case 3 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-08 | 2021-12-08
| Redesign failure case 4 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-08 | 2021-12-08
| Redesign failure case 5 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-08 | 2021-12-08
| Redesign failure case 6 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-08 | 2021-12-09
| Redesign failure case 7 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-08 | 2021-12-09
| Redesign failure case 8 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-09 | 2021-12-09
| Redesign failure case 9 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-09 | 2021-12-09
| Redesign failure case 10 for Archiving sequence diagram | 1 | 2 | Raymond,Brent,Gideon | 2021-12-09 | 2021-12-09
|  | 10 | 20
Logging Implementation |  |  |  | Brent
| Create the MEetAndYou schema and the EventLogs table | 1 | 2 | Brent | 2021-12-10 | 2021-12-10
| Create the users & logins for database | 1 | 2 | Brent | 2021-12-10 | 2021-12-10
| Create & test InsertLog stored procedure in SQL Server DB | 1 | 2 | Brent | 2021-12-10 | 2021-12-10
| Create & test UpdateLog stored procedure in SQL Server DB | 1 | 2 | Brent | 2021-12-10 | 2021-12-10
| Create & test CheckExistingLog scalar-valued function in SQL Server DB | 1 | 2 | Raymond | 2021-12-11 | 2021-12-11
| Create & test GetCurrentIdentity scalar-valued function in SQL Server DB | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Create & test InsteadOfUpdate trigger for EventLogs table | 1 | 2 | Raymond | 2021-12-12 | 2021-12-12
| Write the ILogDAO interface | 1 | 2 | Brent | 2021-12-11 | 2021-12-11
| Write & test the PushLogToDB method for both system & user logs in DAO | 1 | 2 | Brent | 2021-12-11 | 2021-12-11
| Write & test the GetCurrentIdentity method for user logs in DAO | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & test the CheckExistingLogs method for user logs in DAO | 1 | 2 | Brent | 2021-12-11 | 2021-12-11
| Write & test the UpdateLogs method for user logs in DAO | 1 | 2 | Brent | 2021-12-11 | 2021-12-11
| Write the ILoggingService interface | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & test the CreateNewLog method for system logs in LoggingService | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & test the CreateNewLog method for user logs in LoggingService | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & test the MakeLog method for system logs in LoggingService | 1 | 2 | Brent, Raymond | 2021-12-12 | 2021-12-12
| Write & test the MakeLog method for user logs in LoggingService | 1 | 2 | Brent, Raymond | 2021-12-12 | 2021-12-12
| Write & test the PushLogToDB method for both system & user logs in LoggingService | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & test the BeginLogProcess method for system logs in LoggingManager | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & test the BeginLogProcess method for user logs in LoggingManager | 1 | 2 | Brent | 2021-12-12 | 2021-12-12
| Write & execute unit tests for logging success cases (logging system success/failure events, user success/failure events) | 1 | 2 | Brent | 2021-12-11 | 2021-12-12
| Write & execute unit tests for logging failure cases 1-3 | 1 | 2 | Brent | 2021-12-11 | 2021-12-13
| Write & execute unit tests for logging failure cases 4-5 | 1 | 2 | Brent | 2021-12-11 | 2021-12-12
| Modify PushLogToDB method in LogDAO to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify GetCurrentIdentity method in LogDAO to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify CheckExisingLogs method in LogDAO to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify UpdateLogs method in LogDAO to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify both CreateNewLog methods in LoggingService to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify both MakeLog methods in LoggingService to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify PushLogToDB method in LoggingService to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
| Modify both BeginLogProcess methods in LoggingManager to be asynchronous | 1 | 2 | Brent | 2021-12-14 | 2021-12-14
|  | 31 | 62
Archiving Implementation |  |  |  | Raymond
| Create & test GetArchiveCount scalar-valued function in SQL Server DB | 1 | 2 | Raymond | 2021-12-11 | 2021-12-11
| Create & test Logs30DaysOld table-valued function in SQL Server DB | 1 | 2 | Raymond | 2021-12-11 | 2021-12-11
| Create & test DeleteLogsOlderThan30 table-valued function in SQL Server DB | 1 | 2 | Raymond | 2021-12-11 | 2021-12-11
| Write & test ReadLogsOlderThan30 method in LogDAO | 1 | 2 | Brent, Raymond | 2021-12-12 | 2021-12-12
| Write & test DeleteLogsOlderThan30 method in LogDAO | 1 | 2 | Gideon | 2021-12-12 | 2021-12-12
| Write & test GetArchiveCount method in LogDAO | 1 | 2 | Raymond | 2021-12-12 | 2021-12-12
| Creation of ArchiveConfig | 1 | 2 | Gideon | 2021-12-13 | 2021-12-13
| Create variables to acquire specific system directories for buffer location and archive location | 2 | 2 | Gideon | 2021-12-13 | 2021-12-13
| Write IArchiverService | 1 | 2 | Raymond, Brent, Gideon | 2021-12-12 | 2021-12-12
| Write & test GetOldLog method for both user and system logs | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Write & test ConsolidateOldLogs for both user and system logs | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Write & test CompressOldLogs for both user and system logs | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Write & test Compress for both user and system logs | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Write & test DeleteOldLogs for both user and system logs | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Implementation of error handling for nonexistent files | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Write & test ArchiveOldLogs method in ArchiveManager | 1 | 2 | Brent | 2021-12-13 | 2021-12-13
| Write & execute archiving success case | 1 | 2 | Raymond
| Write & execute archiving fail cases 1-3 | 1 | 2 | Brent | 2021-12-13 | 2021-12-13
| Write & execute archiving fail cases 4-6 | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
| Write & execute archiving fail cases 7-10 | 1 | 2 | Raymond | 2021-12-13 | 2021-12-13
|  | 21 | 38 | Raymond, Brent | 2021-12-13 | 2021-12-14
User Management Implementation |  |  |  | Josh
| Create the UserAccountRecords & AdminAccountRecords table | 1 | 1 | Josh, Vivian | 2021-12-04 | 2021-12-04
| Create & test CreateUserRecord stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-04 | 2021-12-04
| Create & test UpdateUserAccountEmail stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-04 | 2021-12-04
| Create & test UpdateUserAccountPassword stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-04 | 2021-12-04
| Create & test UpdateUserAccountPhoneNum stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-04 | 2021-12-04
| Create & test DeleteUserAccountRecord stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-05 | 2021-12-05
| Create & test DisableUserAccountEmail stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-05 | 2021-12-05
| Create & test EnableUserAccountEmail stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-05 | 2021-12-05
| Create & test CreateAdminRecord stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-05 | 2021-12-05
| Create & test UpdateAdminAccountEmail stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-05 | 2021-12-05
| Create & test UpdateAdminAccountPassword stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-06 | 2021-12-06
| Create & test DeleteAdminAccountRecord stored procedure in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-06 | 2021-12-06
| Create & test VerifyUserRecordInDB scalar-valued function in SQL Server DB | 1 | 2 | Josh, Vivian | 2021-12-06 | 2021-12-06
| Create & test VerifyAdminRecordInDB scalar-valued function in SQL Server DB | 1 | 1 | Josh, Vivian | 2021-12-06 | 2021-12-06
| Create UserAccountEntity class object | 1 | 1 | Josh, Vivian | 2021-12-06 | 2021-12-06
| Create AdminAccountEntity class object | 1 | 1 | Josh, Vivian | 2021-12-07 | 2021-12-07
| Create interface for UMDAO | 1 | 1 | Josh, Vivian | 2021-12-07 | 2021-12-07
| Write and test isUserCreated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-07 | 2021-12-07
| Write and test isUserEmailUpdated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-07 | 2021-12-07
| Write and test isUserEmailUpdated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-08 | 2021-12-08
| Write and test isUserPasswordUpdated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-08 | 2021-12-08
| Write and test isUserPhoneUpdated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-08 | 2021-12-08
| Write and test isUserDeleted method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-08 | 2021-12-08
| Write and test isUserDisabled method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-08 | 2021-12-08
| Write and test isUserEnabled method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-09 | 2021-12-09
| Write and test isAdminCreated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-09 | 2021-12-09
| Write and test isAdminEmailUpdated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-09 | 2021-12-09
| Write and test isAdminPasswordUpdated method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-09 | 2021-12-09
| Write and test isAdminDeleted method for UMDAO | 1 | 2 | Josh, Vivian | 2021-12-09 | 2021-12-09
| Write and test isUserInDBVerified method for UMDAO | 1 | 1 | Josh, Vivian | 2021-12-10 | 2021-12-10
| Write and test isAdminInDBVerified method for UMDAO | 1 | 1 | Josh, Vivian | 2021-12-10 | 2021-12-10
| Create interface for UMService | 1 | 1 | Josh, Vivian | 2021-12-10 | 2021-12-10
| Write isUserCreated, isUserEmailUpdated, isUserPasswordUpdated, and isUserPhoneUpdated for UMService | 1 | 1 | Josh, Vivian | 2021-12-10 | 2021-12-10
| Write isUserDeleted, isUserDisabled, isUserEnabled, isAdminCreated for UMService | 1 | 1 | Vivian, Josh | 2021-12-11 | 2021-12-11
| Write isAdminPasswordUpdated, isAdminDeleted, and isAdminInDBVerified for UMService | 1 | 1 | Vivian, Josh | 2021-12-11 | 2021-12-11
| Write and test BeginCreateUser for UMManager | 1 | 1 | Vivian, Josh | 2021-12-11 | 2021-12-11
| Write and test BeginUpdateUserEmail for UMManager | 1 | 1 | Vivian, Josh | 2021-12-11 | 2021-12-11
| Write and test BeginUpdateUserPassword for UMManager | 1 | 2 | Vivian, Josh | 2021-12-11 | 2021-12-11
| Write and test BeginUpdateUserPhone for UMManager | 1 | 2 | Vivian, Josh | 2021-12-12 | 2021-12-12
| Write and test BeginDeleteUserAccount for UMManager | 1 | 2 | Vivian, Josh | 2021-12-12 | 2021-12-12
| Write and test BeginDisableUserAccount for UMManager | 1 | 2 | Vivian, Josh | 2021-12-12 | 2021-12-12
| Write and test BeginEnableUserAccount for UMManager | 1 | 2 | Vivian, Josh | 2021-12-12 | 2021-12-12
| Write and test BeginCreateAdmin for UMManager | 1 | 2 | Vivian, Josh | 2021-12-13 | 2021-12-13
| Write and test BeginUpdateAdminEmail for UMManager | 1 | 2 | Vivian, Josh | 2021-12-13 | 2021-12-13
| Write and test BeginUpdateAdminPassword for UMManager | 1 | 2 | Vivian, Josh | 2021-12-13 | 2021-12-13
| Write and test BeginDeleteAdminAccount for UMManager | 1 | 1 | Vivian, Josh | 2021-12-13 | 2021-12-13
| Write and test IsAdminVerified for UMManager | 1 | 2 | Vivian, Josh | 2021-12-14 | 2021-12-14
| Write and test VerifyUserInfo for UMManager | 1 | 2 | Vivian, Josh | 2021-12-14 | 2021-12-14
| Write and test IsEmailVerified for UMManager | 1 | 2 | Vivian, Josh | 2021-12-14 | 2021-12-14
| Write and test IsPasswordVerified for UMManager | 1 | 2 | Vivian, Josh | 2021-12-14 | 2021-12-14
| Write and test IsPhoneNumVerified for UMManager | 1 | 2 | Vivian, Josh | 2021-12-14 | 2021-12-14
|  | 51 | 88
DAR: Automated Testing |  |  |  | Vivian
| Figure out metrics used for table of analysis | 1 | 2 | Vivian, Josh | 2021-12-10 | 2021-12-10
| Rate xUnit, MSTest, and NUnit metrics | 1 | 2 | Vivian, Josh | 2021-12-10 | 2021-12-10
| Write conclusion to summarize metrics for each automated test framework | 1 | 2 | Vivian, Josh | 2021-12-10 | 2021-12-10
| Create and run tests to compare each automated testing tool | 1 | 2 | Vivian, Josh | 2021-12-10 | 2021-12-10
|  | 4 | 8

## Project Backlog
Name | Priority | Client Due Date | Internal Due Date
Project Proposal/App-Specific Features | 1 | 2021-09-06 | 2021-10-02
Tech Spec | 1 | 2021-10-06 | 2021-10-05
Site Map | 2 | 2021-10-06 | 2021-10-03
BRD | 3 | 2021-10-06 | 2021-10-05
HLD | 4 | 2021-10-06 | 2021-10-05
Test Plan | 1 | 2021-10-27 | 2021-10-23
ProjectPlan | 2 | 2021-10-27 | 2021-10-20
Network Diagram | 3 | 2021-10-27 | 2021-10-17
Milestone 1 Revisions | 1 | 2021-12-08 | 2021-11-08
Tech Approval | 1 | 2021-12-08 | 2021-11-16
LLD Logging | 1 | 2021-12-08 | 2021-11-24
LLD User Management: Single Operation | 2 | 2021-12-08 | 2021-11-24
LLD User Management: Bulk Operation | 1 | 2021-12-08 | 2021-12-02
LLD Archiving | 2 | 2021-12-08 | 2021-12-02
Logging Implementation | 1 | 2021-12-08 | 2021-12-14
Archiving Implementation | 2 | 2021-12-08 | 2021-12-14
User Management Implementation | 3 | 2021-12-08 | 2021-12-14
DAR: Automated Testing | 4 | 2021-12-08 | 2021-12-10
Data Store Access | 1 | 2022-02-06 | 2022-02-06
Documentation | 2 | 2022-02-06 | 2022-02-06
Set up AWS | 3 | 2022-02-06 | 2022-02-06
Suggestions | 4 | 2022-02-06 | 2022-02-06
User Profile Dashboard | 5 | 2022-02-06 | 2022-02-06
Registration | 6 | 2022-04-07 | 2022-04-07
Login/Logout | 7 | 2022-04-07 | 2022-04-07
Error Handling | 8 | 2022-04-07 | 2022-04-07
Hyperlink Sharing | 9 | 2022-04-07 | 2022-04-07
Rating System | 10 | 2022-04-07 | 2022-04-07
Localized Weather Forecast | 11 | 2022-04-07 | 2022-04-07
Usage Analysis Dashboard | 12 | 2022-04-22 | 2022-04-22
User Access Control | 13 | 2022-04-22 | 2022-04-22
Memory Album | 14 | 2022-04-22 | 2022-04-22
Duplicating Itineraries | 15 | 2022-04-22 | 2022-04-22